## Front Cover
Nether Edge Developments
Planned Preventative Maintainance
22 August 2019

## Summary
Location | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Total Building Cost
Sheaf 1 | 4500 | 28175 | 525 | 15525 | 9025 | 3725 | 1775 | 675 | 179750 | 243675
Sheaf 2 | 3750 | 35350 | 0 | 4250 | 8300 | 13250 | 4250 | 8300 | 192050 | 269500
Sheaf 3 | 3000 | 1000 | 17900 | 500 | 5000 | 1500 | 10500 | 1000 | 16000 | 56400
Alexandra | 3870 | 21750 | 500 | 0 | 1900 | 1000 | 21250 | 0 | 21400 | 71670
Muxlow | 825 | 2500 | 39300 | 3000 | 0 | 11300 | 27000 | 3000 | 56100 | 143025
Kingswood Central | 6750 | 2000 | 2750 | 13250 | 16750 | 9000 | 4000 | 7500 | 35250 | 97250
Victoria | 500 | 4650 | 4500 | 19750 | 2500 | 8150 | 0 | 14250 | 29150 | 83450
Cliffe | 0 | 4500 | 24650 | 19550 | 0 | 2500 | 29650 | 3000 | 10300 | 94150
Pevrill | 0 | 500 | 36500 | 0 | 13000 | 0 | 16250 | 0 | 20750 | 87000
Edward | 400 | 15200 | 0 | 3500 | 300 | 0 | 3750 | 0 | 5500 | 28650
Garages | 8950 | 2550 | 1750 | 1750 | 1750 | 2050 | 5700 | 1750 | 4500 | 30750
Hardstandings | 800 | 4000 | 550 | 8500 | 8550 | 1000 | 550 | 4000 | 47600 | 75550
Boundaries
Total | 33345 | 122175 | 128925 | 89575 | 67075 | 53475 | 124675 | 43475 | 618350 | 1281070
Notes
Our prices have been based on tendered rates, and are assumed to be undertaken by a main contractor utilising the correct working methods, to the relevant standards and statutory requirements. All costs are Net of VAT.

## Sheaf 1
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only alternative
Planned Maintenance Schedule - Sheaf 1
Item Ref. | Element / Location | Condition and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition, some slipped and damaged tiles noted to the front and rear. The tiles are generally soiled | B | Allow for safe access to undertake repairs to slipped slates and carry out a general roof inspection. | 2CI |  | 20000 | [7 empty] | Repairs to the roof covering will require scaffolding. We recommend that works are grouped together across the roof to make the cost of scaffold erection efficient.
1.2 | Roof | Concrete ridge tiles bedded on cement mortar. Algae growth noted. Missing pointing noted. | B | Remove the existing ridge tiles, scrape existing mortar off and re bed with a new dry ridge system. Clear algae growth off ridge tile. | 2CI |  | 4300 | [7 empty] | Access costs included above
1.3 | Roof | Lead valley gutters. No defects identified. Mortar debris has collected on the standing seam lead flat roof. | B | Clear debris off flat roof. Allow for access included in the above costs. | 2CI |  | Incl | [7 empty] | Access costs included above
1.4 | Roof | Assumed artificial stone parapet gable walls. | B | Appear to be in fair condition from the footage, however check the mechanical fixings (Pull test) within the reporting term once access is available for ridge replacement. | 1BIII |  | 1000 | [7 empty] | Allowance for professional consultant opinion.
1.5 | Roof | Inverted flat roofs to balcony's. Leaking noted to the internal communal areas (above window) believed to be a result of a roof leak from the above flat roof balcony to the west elevation. | D | No access obtained onto the individual balconies to undertake further investigation. Ballast and assumed insulation below will need to be removed so the waterproofing element can be reviewed. | 1CII | 2500 |  | tbc | [6 empty] | Investigation works required. Who is responsible for maintenance of the roof? Cost allows for investigations, report and works.
1.6 | Smoke vent | No detail could be obtained from aerial footage. | B | Check condition upon access being obtained for ridge replacement. |  |  | Incl
1.7 | Rainwater goods | Powder coated pressed aluminium gutters and hoppers. Fading noted to coating and some joints appear to be leaking. | B | Allow for all joints to downpipes (detach and reconnect) and gutters to be resealed. | 1CI |  | 850 | [7 empty] | Access costs included above
1.8 | Rainwater goods | uPVC downpipe. Fair condition. | B | No works anticipated.
1.9 | Facias and Soffits | Painted Timber. Poor condition paint flaking. | B | Allow for cyclical decorations. | 2CI |  | 2000 |  |  |  | 3200 |  |  | 6400 | Access included with scaffolding in 2021 and from hoists thereafter
1.1 | Drainage goods | Painted iron soil pipe are in a poor decorative condition. | B | Allow for cyclical decorations. | 2CI |  | Incl |  |  |  | Incl |  |  | Incl
2 | WALLS
2.1 | Walls | Re-constituted walling stone. Black staining to external staircase wall. Sporadic missing pointing. Pointing missing to window heads and sills | B | Allow for minor repointing. Allow for new mastic joints at lintel joint lines. | 1CI | 1500 | [7 empty] | 1500 | Allowance for works from a hoist or temporary scaffold tower.
2.2 | Walls | Polysulphide mastic expansion joint. Fair condition. | B | Consider replacing as and when they become brittle. | 2CI | [7 empty] | 100
2.3 | Walls | Steel window lintels. Some minor surface corrosion noted. | B | Wire brush the lintel and apply rust inhibitor prior to redecorating. Thereafter undertake cyclical redecoration. | 2CI | [8 empty] | Incl | We recommend works are undertaken when the windows are replaced.
2.4 | Walls | Art stone/concrete window heads and sills. Hairline cracks observed centrally to numerous window heads (circa 30no.) Pointing repairs needed to heads and sills. | B | Monitor cracking. Repoint areas around heads and sills. | 2CI | [9 empty] | Consider works are required but less likely to be undertaken until defects progress further. Consider specialist advice for stone repairs. Works can be undertaken during window replacement.
3 | WINDOWS AND DOORS
3.1 | Windows North | Powder coated aluminium windows. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 1CI |  |  |  | 2500 |  |  |  |  | 25000 | We have allowed for wholesale replacement. Works can be undertaken to re coat the windows however, we believe replacements will be required in 10 years and we have therefore allowed for maintaining the appearance in the interim. Cost included in years where scaffold available.
3.2 | Windows East | Powder coated aluminium windows. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 1CI |  |  |  | 3500 |  |  |  |  | 35000
3.3 | Windows South | Powder coated aluminium windows. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 1CI |  |  |  | 2500 |  |  |  |  | 25000
3.4 | Windows West | Powder coated aluminium windows. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 1CI |  |  |  | 3500 |  |  |  |  | 35000
3.5 | Door North | Timber door. Fair condition. | B | Allow for cyclical decorations. | 2CI |  |  | 150 |  |  | 150 |  |  | 300
3.6 | Curtain wall and doors East & West elevations | Powder coated aluminium frames. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and coating. General repairs to the mastic seals where the frame abuts the stonework. | 2CI |  |  |  | 3500 |  |  |  |  | 40000
3.7 | Spandrel Panels Ground floor North | Timber spandrel panels to the ground floor. Fair condition. | B | Allow for cyclical decorations. | 2CI |  |  | 350 |  |  | 350 |  |  | 700
3.8 | Ventilation louvers to Ground floor West | Powder coated aluminium vents. Soiled but in fair condition. | B | Allow for cleaning and coating. | 2CI |  |  | Incl |  |  | Incl |  |  | Incl
4 | EXTERNAL STAIRCASE
4.1 | Flagstone hardstanding's | Soiled but in fair condition. | B | Allow for cyclical jet washing to flagstones. | 1BI |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 100
4..2 | Upstand | Vegetation noted to the upstand to the paving flags on the staircase. | B | Allow for removing vegetation to prevent penetration of waterproofing membrane. | 1CI |  | Incl | Incl | Incl | Incl | Incl | Incl | Incl | Incl
5 | INTERNALLY (LEISURE CENTRE)
5.1 | Floor covering | Tiled ceramic flooring to reception, changing rooms, hallways. Fair condition. | B | No works required subject to aesthetic requirements and reactive works. | 2CI | [9 empty] | Consider no works required over 10 years. Consideration to future costs for wholesale replacement may be required based upon future appearance.
5.2 | Floor covering | Barrier matting to entrance. Fair condition. | B | Replace periodically depending on use. | 2CI | [7 empty] | 300
5.3 | Floor covering | Vinyl floor in studio. Cracking noted to vinyl floor. | B | When the vinyl is replaced, a joint needs to be inserted along the building line to prevent the same issue occurring. Consider this is an aesthetic issue and therefore immediate replacement is not required. | 2CI | [9 empty] | This will last 10 years but you may wish to consider costs based upon use and appearance.
5.4 | Floor covering | Vinyl flooring in staffroom. Fair condition. | B | Replace periodically depending on use. | 2CI | [8 empty] | 250
5.5 | Floor covering | Carpeted raised floor in gym. Fair condition. | B | Replace periodically depending on use. | 2CI | [8 empty] | 1500
5.6 | Walls | Painted plastered walls throughout reception areas, hallways, gym, staff room, studio and bulkheads to the gym area. Fair condition. | B | Allow for cyclical decorations. | 2CI |  |  |  |  | 8500 |  |  |  | 8500
5.7 | Walls | Tiled walls to changing rooms. | B | Allow for cyclical cleaning and re-grouting where required. | 3C |  |  |  |  | 500 |  |  |  | 500
5.8 | Suspended ceiling | Mineral fibre ceiling to reception areas. Fair condition. | B | No works anticipated. | 3C | [9 empty] | This will last 10 years but you may wish to consider costs based upon use and appearance.
5.9 | Suspended ceiling | Moisture resistant ceiling tiles to changing rooms, gym and studio. Fair condition. | B | No works anticipated. | 3C | [9 empty] | This will last 10 years but you may wish to consider costs based upon use and appearance.
5.1 | Internal doors | Plastic coated timber fire doors. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500
5.11 | Lift | No works included as specialist report required. |  | NA
5.12 | Swimming pool and Jacuzzi | Not surveyed as specialist reports required. |  | NA
5.13 | Staff room | Kitchenette in fair condition. | B | Allowance for adhoc minor repairs | 3CI | [7 empty] | 250
6 | INTERNALLY (COMMUNAL AREAS)
6.1 | Floor covering | Carpeted floor. Fair condition. | B | Replace when required | 3CI | [6 empty] | 1750
6.2 | Stairs | Stainless steel handrail with glazed infill panels. Fair condition. | B | No works anticipated
TOTALS: | [5 empty] | 4500 | 28175 | 525 | 15525 | 9025 | 3725 | 1775 | 675 | 179750

## Sheaf 2
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only alternative
Planned Maintenance Schedule - Sheaf 2
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition 2no slipped slates across the roof. The tiles are generally soiled. | B | Allow for safe access to undertake repairs to 2no slipped slates and carry out a general roof inspection. | 2CI |  | 20000 | [7 empty] | Repairs to the roof covering will require scaffolding. We recommend that works are grouped together (ridge works) across the roof to make the cost of scaffold erection efficient.
1.2 | Roof | Concrete ridge tiles bedded on cement mortar. Numerous loose tiles and missing mortar sections visible throughout the roof. | B | Remove the existing ridge tiles, scrape existing mortar off and re bed with a new dry ridge system. | 1CI |  | 4800
1.3 | Roof | Fibre glass roof covering to the entrance lobby's to each core. No defects noted as recently replaced. | A
1.4 | Roof | Lead valleys and dormers. Satisfactory condition throughout. | B
1.5 | Roof | Concrete coping & kneeler stones. SW elevation coping stones have been over clad with leadwork / liquid waterproofing. | B | A pull test is recommended during routine maintenance of this roof. This will ensure no loose stonework. | 1BIII |  | 1000 | [7 empty] | Query why works have been undertaken to cover coping stones with lead?
1.6 | Roof | Inverted flat roofs to balcony's. Algae growth evident to the concrete flag covering. | B | Clean down flags as part of on going maintenance. | 3CI |  |  |  | 750 |  |  | 750 |  |  | Confirm if balcony's are communal responsibility.
1.7 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and downpipes. Water leakage is evident through staining to joint lines throughout. | B | Allow for all joints to downpipes and gutters to be re sealed. | 1CI |  | 1250 | [6 empty] | 3000 | No provision allowed for accessing the rear downpipes within gardens.
1.8 | Rainwater goods | Presumed lead valley at high level collecting water discharge from the roof pitches. | [12 empty] | Drone footage not clear on the valley detail due to the size of the opening visible.
1.9 | Fascia's & Soffits | Painted timber. Commensurate with age. | B | Allow for cyclical decorations. | 1CI |  |  |  | 3500 |  |  | 3500 |  | 3500 | Access platform allowed for 2no gable elevations.
2 | WALLS
2.1 | Walls North | Re-constituted walling stone coupled with art stone window cills. Isolated areas of missing pointing at low level. Soiled cills. | B | Allow for repointing at low level. | 1CI | 1000 |  |  |  |  | 1000
2.2 | Walls North | Render infill sections surrounding glazing. Paint finish stained and nearing re paint decision time. | B | Allow for cyclical redecoration. | 2CI |  | 3000 |  |  | 3000 |  |  | 3000 | 3000
2.3 | Walls East | Re-constituted walling stone coupled with art stone window cills. Stepped cracking evident from window lintel to RHS. Existing window lintel appears to be under overdue stress from load. This has caused the stepped cracking to the area. | B | Monitor for further movement as the issue does not appear to be detrimental to the structure. | 1BI | 500
2.4 | Walls East | Render infill sections surrounding glazing. Paint finish stained and nearing re paint decision time. | B | Allow for cyclical redecoration | 2CI |  | 300 |  |  | 300 |  |  | 300 | 300 | Mobile access included in North Elevation
2.5 | Walls South | Re-constituted walling stone coupled with art stone window cills. Soiled cills. No defect. | [12 empty] | No access available to rear of dwellings.
2.6 | Walls South | Render infill sections surrounding glazing. Paint finish stained and nearing re paint decision time. | B | Allow for cyclical redecoration | 2CI |  | 2500 |  |  | 2500 |  |  | 2500 | 2500 | Tower scaffold allowed.
2.7 | Walls West | Re-constituted walling stone coupled with art stone window cills. Soiled cills. No defect.
2.8 | Walls West | Render infill sections surrounding glazing. The existing paint finish is deteriorated. | B | Allow for cyclical redecoration | 2CI |  | 2500 |  |  | 2500 |  |  | 2500 |  | Scaffold access allowed.
3 | WINDOWS & DOORS
3.1 | Windows North | Powder coated aluminium window casements. Double glazed units. Powder coating showing early onset of failure particularly around mitre joints. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 2CI | [8 empty] | 60000 | Rate per window is circa £100 if scaffolding is errected. We advise this be carried out for aesthetic improvements only. We have allowed for wholesale replacement in yr 2027. Works can be undertaken to re coat the windows however, we believe replacements will be required in 10 years and we have therefore allowed for maintaining the appearance in the interim.
3.2 | Curtain wall & Doors North | Powder coated aluminium frames. Double glazed units. Satisfactory condition commensurate with age. | B | Allow for cleaning and coating. General repairs to the mastic seals where the frame abuts the stonework. | 2CI | [8 empty] | 35000
3.3 | Windows East | Powder coated aluminium window casements. Double glazed units. Powder coating showing early onset of failure particularly around mitre joints. Window seals have displaced to isolated casements. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. Isolated window seal replacements will be required. | 2CI | 500 | [7 empty] | 8000
3.4 | Windows South | Powder coated aluminium window casements. Double glazed units. Powder coating showing early onset of failure particularly around mitre joints. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 2CI | [8 empty] | 60000 | No access was available to the rear of the building. It would be sensible to assume that the same comments apply from the remaining elevations.
3.5 | Doors South | Powder coated aluminium frames. Double glazed units. Satisfactory condition | B | Allow for cleaning and coating. General repairs to the mastic seals where the units abut the stonework. | 2CI | 500 | [7 empty] | 4500
3.6 | Windows West | Powder coated aluminium window casements. Double glazed units. Powder coating showing early onset of failure particularly around mitre joints. | B | Allow for cleaning and polishing the windows with aluminium colour restorer in the short term. Wholesale replacement should be considered within 10 years. | 2CI | [8 empty] | 7000 | We have allowed for wholesale replacement. Works can be undertaken to re coat the windows however, we believe replacements will be required in 10 years and we have therefore allowed for maintaining the appearance in the interim.
4 | M&E
4.1 | Lighting | Surfaced fixed background lighting. Satisfactory condition. | B | Consider replacement within 10 years. | 2CII | [8 empty] | 2000 | Many of these fittings were not inspected due to restricted access to dwellings.
5 | INTERNALLY
5.1 | Decoration (Core 1) | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. | 2CI | [5 empty] | 1750 |  |  | 1750
5.2 | Floor covering (Core 1) | Ribbed carpet covering. Satisfactory condition. | B | Advise replacement will be required over the next 10 years. | 2CI | [5 empty] | 4500
5.3 | Joinery (Core 1) | Veneer finished timber fire exit doors. Satisfactory condition. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs. | 1BIII | 750
5.4 | Decoration (Core 2) | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. | 2CI | [5 empty] | 1500 |  |  | 1500
5.5 | Floor covering (Core 2) | Ribbed carpet covering. Satisfactory condition. | B | Advise replacement will be required over the next 10 years. | 2CI | [5 empty] | 4500
5.6 | Joinery (Core 2) | Veneer finished timber fire exit doors. Satisfactory condition. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500
TOTALS: | [5 empty] | 3750 | 35350 | 0 | 4250 | 8300 | 13250 | 4250 | 8300 | 192050

## Sheaf 3
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Sheaf 3
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition but tiles are excessively soiled. | B | Allow for hoist access to undertake periodic isolated repairs. | 2CI |  | 500 |  | 500 |  | 1500 |  | 500 | 1000 | Minor allowance for ad hoc repairs should they be required in future years.
1.2 | Roof | Concrete ridge tiles bedded on cement mortar. Generally in a fair condition, yet isolated repairs have been undertaken. | B | We expect ridge pointing and general maintenance over the reporting period and given the costs to scaffold the building, we recommend the ridge is replaced with a dry ridge system. | 2CI |  |  | 15000 | [6 empty] | Allowance for scaffolding.
1.3 | Roof | Lead valleys and dormers. Satisfactory condition throughout. |  | No works anticipated. | 3CII
1.4 | Roof | Stone coping & kneeler stones. The coping stones in parts have been over clad with leadwork, not clear if this is original or repairs undertaken in recent years. | B | Cracking noted in the some coping stones to east elevation, appears minor and no works anticipated. | 2CI | [9 empty] | Query why works have been undertaken to cover coping stones with lead?
1.5 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and downpipes. Gutter leak noted to the south elevation. Foliage growth noted to the middle section of the elevation facing the roadside. | B | Allow for repairing the gutter with jointing and sealing compound. Allow for wholesale sealing works in future years. Clean gutters in year 1. | 1CI |  |  | 850
1.6 | Fascia's & Soffits | Painted timber soffits and facia, rotting in a small section . | B | Allow for cyclical decorations, starting in year 1 to prevent further deterioration. | 1CI |  |  | 2000 |  |  |  | 8500 |  | 8500 | Costs increases in future years for access (without full scaffolding which is included in 2021)
1.7 | Skylights | 4no. Fixed glazed roof lights. The material used can not be confirmed by drone footage. | B | Debris trapped at the head of the window requires removal when access is available. | 1CI |  |  | 50
2 | WALLS
2.1 | Walls North | Pitched face natural stone with art stone window cills and lintels, kneelers and copings to the gables of the projecting roofs. | B | Allowance for undertaking isolated pointing over the reporting period. Mastic to lintels and cills could be undertaken to limit future maintenance. | 2CI |  | 500 |  |  | 500 |  |  | 500 | 500 | General allowance for pointing works.
2.2 | Walls East | Pitched face natural stone with art stone window cills and lintels, kneelers and copings to the gables of the projecting roofs. | B | Allowance for undertaking isolated pointing over the reporting period. Mastic to lintels and cills could be undertaken to limit future maintenance. | 2CI |  | Incl |  |  | Incl |  |  | Incl | Incl
2.3 | Walls South | Pitched face natural stone with art stone window cills and lintels, kneelers and copings to the gables of the projecting roofs. | B | Allowance for undertaking isolated pointing over the reporting period. Mastic to lintels and cills could be undertaken to limit future maintenance. | 2CI |  | Incl |  |  | Incl |  |  | Incl | Incl
2.4 | Walls West | Pitched face natural stone with art stone window cills and lintels, kneelers and copings to the gables of the projecting roofs. | B | Allowance for undertaking isolated pointing over the reporting period. Mastic to lintels and cills could be undertaken to limit future maintenance. | 2CI |  | Incl |  |  | Incl |  |  | Incl | Incl
3 | WINDOWS
3.1 | Windows North | Powder coated aluminium, double glazed window units. Window frame and glass are slightly soiled. | B | Allow for cleaning and polishing the windows with aluminium colour restorer. | 2CI | [9 empty] | We do not consider these units to need replacement over the coming 10 year period. Therefore, suggest a rate per window of circa £100 to polish and coat. We advise this be carried out for aesthetic improvements as and when scaffold is erected.
3.2 | Windows East | Powder coated aluminium framed, double glazed window units. | B | Allow for cleaning and polishing the windows with aluminium colour restorer. | 2CI | [9 empty] | As above
3.3 | Windows South | All windows are powder coated aluminium, which is prone to fading over time. | B | Allow for cleaning and polishing the windows with aluminium colour restorer. | 2CI | [9 empty] | As above
3.4 | Windows West | Powder coated aluminium framed double glazed awning window units. Generally soiled. | B | Allow for cleaning and polishing the windows with aluminium colour restorer. | 2CI | [9 empty] | As above
4 | Doors
4.1 | Doors South | 2No. Powder coated aluminium doors to communal areas with 2 glass panels in each. Each door has glazed infill panels around the sides at top. The door to communal 1 is tied incorrectly to the building and the frame is detaching. We assume the windows are secured to the art stone rather than the stone behind, which has caused the art stone to move. | C | Allow for redecoration periodically. Take out the door to Communal 1 and resecure the frame. Point up the art stone jambs. | 1CIII | 2500
4.2 | Doors South | 4No. Timber veneered external doors, with timber frame and glass infill panels to the top and both sides. Doors are fading especially around the bottom rail. Also the timber frames around the doors are beginning to rot and the paint is flaking away. | B | Redecoration required in year 1 and cyclical thereafter. | [10 empty] | Unsure who is responsible for maintenance of the individual doors.
4.3 | Lighting | 2No. LED floodlights, 4No. Circular lights next to entrance doors and 2No. Intruder alarm bell boxes. | B | Allowed a provisional sum for ad hoc replacement over 10 years | 2CI | [6 empty] | 2000 |  |  | Provisional sum
5 | INTERNALS - COMMUNAL AREAS
5.1 | Decoration | Painted plaster finish and joinery in good condition. | B | Redecorate periodically. | 2CI |  |  |  |  | 1500 |  |  |  | 3000
5.2 | Flooring | Small section of barrier matting at the entrance is in good condition, carpet to other areas is in fair condition throughout, showing minor signs of wear. | B | Replace periodically. | 2CI |  |  |  |  | 3000 |  |  |  | 3000
5.3 | Joinery | Timber veneered fire doors with stainless steel handles. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500
TOTALS: | [5 empty] | 3000 | 1000 | 17900 | 500 | 5000 | 1500 | 10500 | 1000 | 16000

## Alexandra
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Alexandra
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition however slight soiling. 1No slipped slate within gutter to east elevation. | B | Reinstate 1No tile but consider no substantial works anticipated within the reporting years. | 2CI | 500 |  | 500 |  | 500 |  | 500 |  | 1000 | Minor allowance for ad hoc repairs should they be required in future years.
1.2 | Roof | Concrete ridge tiles have been repaired using a dry ridge system which appears in good order. No works anticipated over the reporting years. | B | Slight algae growth. No works anticipated within the reporting years
1.3 | Roof | Lead valleys are in satisfactory condition throughout. | B | No works anticipated within the reporting years
1.4 | Roof | Artificial stone coping & kneeler stones. | B | No works anticipated within the reporting years | [10 empty] | If access is available in future years, allow for undertaking a pull test to the copings.
1.5 | Roof | 3No stone chimney stacks, general soiling but appear in satisfactory condition. Tops of 1No chimney is coated in a liquid applied paint coating. | B | Allowance for pointing works doing reporting years. | 2CI |  |  |  |  | 1400 |  |  |  | 1400
1.6 | Rainwater goods | Painted steel downpipes to below ground drainage. Concealed seamless gutters to roof. | B | Allow for repairing the gutter with jointing and sealing compound and undertaking cyclical redecoration. | 2CI | [5 empty] | 1000 |  |  | 250
1.7 | Rainwater goods | Gutter leak noted to the east elevation to the top left hand corner. | B | Undertake localised sealing. | 1CI | 200
2 | WALLS
2.1 | Walls | York stone coupled with dressed stone window reveals and cills. Isolated areas of missing pointing at low level. The stone is delaminating and large sections of pointing is missing. Replacement pointing has used portland cement and this requires removal as it is a contributing factor to the stone decay. | C | Allow for undertaking 20m2 of repointing works to remove the portland cement. Thereafter Investigate further with stone specialist such as. (Medusa Stone - Nick Laurence nicklaurence@medusastonemasonry.com). Stone replacements or repairs may be most cost efficient but a specialist is required due to the severity on this building. | 1CI | 450 | [8 empty] | No cost allowed as further investigation work is required. We advise this is sort asap to prevent further deterioration.
2.2 | Walls | Air vent blocked to the north elevation by foliage growth. | B | Remove foliage and ensure vents remain clear. | 1CI | 20
3 | WINDOWS
3.1 | Windows | Double glazed timber top hung opening casement, paint work deteriorating and requires decorating now to limit future costs. | B | Generally in a fair condition. Cyclical decorations required commencing in 2020. | 1CI |  | 11250 |  |  |  |  | 11250 |  | 11250 | Allowance for scaffold tower, thorough preparation and redecoration
3.2 | Doors | Solid timber door and half leaf to entrances and picture doors/windows to the east elevation from the individual residencies. | B | Undertake cyclical redecoration commencing in 2020. | ICI |  | Incl |  |  |  |  | Incl |  | Incl
4 | M&E
| Lighting | Surfaced fixed background lighting. Satisfactory condition. | A | Provisional sum for future replacement | 2BI | [6 empty] | 2000
| Lighting | Exposed cabling coiled up on east elevation, assume light removed. | C | Add replacement light fitting. | 1BIII | 200
INTERNALLY
North core
| Meter cupboard | Dry rot evident to the board behind the meters and brickwork. | C | Extent of cause of rot is unknown due to closure of the below ground floor. Extent of rot may be occurring elsewhere in the void. Locally, works include removal of the meter and replace the backing board. Clean brickwork with anti fungal wash and introduce ventilation | 1BI | 1500 | [8 empty] | Undertake more intrusive survey
| Decoration | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. |  |  | 3750 |  |  |  |  | 3750 |  | 3750
| Floor covering | Ribbed carpet covering. Fair to poor condition. | B | Advise replacement will be required within the next 5 years. |  |  | 1500
| Joinery | Painted timber doors, dado rails, skirting and staircase strings. Satisfactory condition. | B | Undertake cyclical decoration. We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500 | Incl |  |  |  |  | Incl |  | Incl
| Staircase | Painted steel handrails and balustrades. | B | Undertake cyclical decoration |  |  | Incl |  |  |  |  | Incl |  | Incl
South Core
| Decoration | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. |  |  | 3750 |  |  |  |  | 3750 |  | 3750
| Floor covering | Ribbed carpet covering. Fair to poor condition. | B | Advise replacement will be required within the next 5 years. |  |  | 1500
| Joinery | Painted timber doors, dado rails, skirting and staircase strings. Satisfactory condition. | B | Undertake cyclical decoration. We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500 | Incl |  |  |  |  | Incl |  | Incl
| Staircase | Painted steel handrails and balustrades. | B | Undertake cyclical decoration |  |  | Incl |  |  |  |  | Incl |  | Incl
TOTALS: | [5 empty] | 3870 | 21750 | 500 | 0 | 1900 | 1000 | 21250 | 0 | 21400

## Muxlow
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule Muxlow
Item Ref. | Element / Location | Condition and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | COMMENTS
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition however slight soiling. 1No. Slip slate recorded. | B | Replace missing slate with new assume more will be required during reporting years. | 2CI |  | 2500 |  | 2500 |  | 2500 |  | 2500 | 10000 | Minor allowance for ad hoc repairs should they be required in future years.
1.2 | Roof | Concrete ridge tiles have been repaired using a dry ridge system in parts. Hip ridges (assume clay) appear to be on original cement mortar. All appear in good order. | B | Slight algae growth. No works anticpated within the reporting years | 3CII
1.3 | Roof | Lead valleys appear to vary in condition across the roof. | B | Allowance for repairs during the reporting years. | 1CI |  |  | 2000 |  |  | 2000 |  |  | 6000 | Works to coincide with slate replacements as required.
1.4 | Roof | Stone coping & kneeler stones. | B | Undertake pull test when access is available, and undertake isolated pointing. | 1CI |  |  | 500 |  |  | 500 |  |  | 1000 | If access is available in future years, allow for undertaking a pull test to the copings.
1.5 | Roof | 4No stone chmineys across the roof. Repairs aparent to the north pitch elevation to the flaunching of a chimney. | B | Given repairs to one chimney, we assume repairs will be required to the remaining chimneys during the reporting years. | 1CI |  |  | 1800 |  |  | 1800 |  |  | 3600
1.6 | Skylights | 7No velux type rooflights to the north pitch. Appear aluminium from drone footage. | B | No works anticpated during the reporting years. | 2CI
1.7 | Rainwater goods. | Pressed aluminium gutters, appear in good order and recently replaced? | A | No works anticipated. | [10 empty] | Item to be confirmed by committee
1.8 | Rainwater goods. | Painted steel downpipes. Fixings for a bracket are detached from the wall downpipe is ditsorted. | B | Reaffix fixings to the wall so the downpipe is in the correct place. Undertake cyclical decorations. | 1CI | 150 | [8 empty] | Cost for decorations included with window works
2 | WALLS
2.1 | Walls North | York stone coupled with dressed stone window lintels and cills. Isolated areas of missing pointing at low level. The stone is delaminating and large sections of pointing is missing. Replacement pointing has used portland cement and this requires removal as it is a contributing factor to the stone decay. | C | Investigate further with stone specialist such as. (Medusa Stone - Nick Laurence nicklaurence@medusastonemasonry.com). Stone replacements or repairs may be most cost efficient but a specialist is required due to the severity on this building. | 1CI | [9 empty] | No cost allowed as further investigation work is required. We advise this is sort asap to prevent further deterioration.
| Walls East | As above. |  | As above.
| Walls South | As above. |  | As above.
| Walls West | As above. |  | As above.
3 | WINDOWS
3.1 | Windows North | Timber, double glazed bottom hung opening casements. Trickle vents present. Condition satisfactory. | B | Cyclical decorations required commencing in 2021. Mortar raked out of joint lines and replaced with mastic. | 1CI |  |  | 11000 |  |  |  | 11000 |  | 11000 | When the replacement of casements are required, ensure they are in accordance with guidance from Historic England and the planning department. The building adjacent (Kingswood) is Grade II listed and this may pose restrictions on Muxlow.
3.2 | Windows West | Timber, double glazed bottom hung opening casements. Trickle vents present. Condition satisfactory. | B | Cyclical decorations required commencing in 2021. | 1CI |  |  | 3500 |  |  |  | 3500 |  | 3500
3.3 | Windows South | Timber, double glazed bottom hung opening casements. Trickle vents present. Condition satisfactory. | B | Cyclical decorations required commencing in 2021. | 1CI |  |  | 10500 |  |  |  | 10500 |  | 10500
4 | DOORS
4.1 | Doors North | Solid core timber painted door and frame. | B | Cyclical re decoration required. | 1CI |  |  |  | 150 |  |  |  | 150 | 150
4.2 | Doors South | 3No. Solid core timber painted doors and frames. | B | Cyclical re decoration required. Section of timber threshold has significant timber decay and requires replacement to LHS door. | 1CI | 175 |  |  | 350 |  |  |  | 350 | 350
5.0 | M&E
5.1 | Lighting | Surfaced fixed background lighting. Satisfactory condition. | A | Provisional sum for future replacement. | 2BI | [6 empty] | 2000 |  |  | Provisional sum
6 | INTERNALS
6.1 | Decoration | The walls & ceiling are a combination of exposed solid stone and a painted plaster finish. Both finishes are in fair condition. | B | Undertake cyclical decoration. | 2CI |  |  | 4500 |  |  | 4500 |  |  | 4500
6.2 | Floors | Carpet floor covering with entrance barrier matting upon entry point. | B | Allow for periodic replacement. | 2CI |  |  | 5500 | [5 empty] | 5500
6.3 | Joinery | Painted double leaf timber fire doors. | B | Undertake cyclical decoration. We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500 |  |  |  |  | incl |  |  | incl
TOTALS: | [5 empty] | 825 | 2500 | 39300 | 3000 | 0 | 11300 | 27000 | 3000 | 56100

## Kingswood
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Kingswood Central
Item Ref. | Element / Location | Condition and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
| EXTERNALLY | [13 empty] | Only the central core of the building was surveyed as requested.
1 | ROOF
1.1 | Roof | Natural slate roof covering. In part with a flat section at ridge height that is coated with a liquid waterproofing system. The roof to the central area is flat in nature and appears to be an inverted roof with a timber deck. | B | No obvious defects. Reactive defects only presumed during reporting years. | 2CI |  | 1750 |  | 1750 |  | 1750 |  | 1750 | 4000
1.2 | Roof | 2no flat roof balcony's noted. The North deck has recently been recovered and is in good condition. The South deck appears to be in satisfactory condition but the ariel footage is not too clear. |  | No works expected during the reported term to the North deck. The South deck requires closer inspection to be able to comment further. | [10 empty] | Extent of tenants ownership to be confirmed.
1.3 | Roof | Lead valleys appear satisfactory condition throughout. SW corner has a dislodged flashing evident. The projected gable to the North elevation also has significant detached leadwork and is choked in the valley. | C | Undertake isolated repair works as described. | 1CI | 3750 |  |  | 3750 |  |  | 3750 |  |  | Advise annual drone footage commissioned to monitor likely ongoing roof defects. Figure inputted to forecast for repairs.
1.4 | Roof | Concrete ridge tiles have been repaired using a dry ridge system . Appear in good order. | B | Slight algae growth. No works anticpated within the reporting years | 3CII
1.5 | 1.7 | Stone coping & kneeler stones. No defect noted. | B | No defects identified from aerial footage. Recommend pull test when safe access equipment is available. | 2CI |  |  |  | 1000
1.6 | Skylights | 6No Velux type rooflights to the north, east & south pitch. Appear aluminium from drone footage. Central smoke vent over the stair core evident. No visible defects from footage. | B | No works anticipated during the reporting years. | 2CI
1.7 | Chimneys | Dressed stone construction with a combination of pointed stone crowns and flaunched tops. Generally in satisfactory condition through out . | B | Undertake regular review with access imagery. | 2CI
1.8 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and steel downpipes. Water leakage is evident through staining to the downpipes to joint lines. Coating to downpipes are faded. | B | Allow for all joints to downpipes to be re sealed. | 1CI | 2500 |  |  |  |  | 2500 |  |  | 2500 | MEWP access allowed for.
1.9 | Fascia's & Soffits | Painted timber fascia. Commensurate with age. | B | Allow for cyclical decorations. | 1CI |  |  | 2500 |  |  | 2500 |  |  | 5000
2 | WALLS
2.1 | Walls general | York stone coupled with dressed stone window lintels and cills. Isolated areas of missing pointing at low level. The stone is delaminating and large sections of pointing is missing. Replacement pointing has used portland cement and this requires removal as it is a contributing factor to the stone decay. | C | Investigate further with stone specialist such as. (Medusa Stone - Nick Laurence nicklaurence@medusastonemasonry.com). Stone replacements or repairs may be most cost efficient but a specialist is required due to the severity on this building. | 1CI | [9 empty] | No cost allowed as further investigation work is required. We advise this is sort asap to prevent further deterioration.
2.2 | Lightning Protection | Copper lightening protection. Noted. | B
2.3 | Entrance Steps | Stone steps. Soiling evident. | B | Allow for cyclical jet washing. | 1BIII |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 750
3 | WINDOWS AND DOORS
3.1 | Windows | Timber framed double glazed windows. In fair condition. | B | Allow for cleaning of windows and cyclical redecoration. | 1CI |  |  |  |  | 16500 |  |  |  | 16500
3.2 | Bay Windows East Elevation | Timber framed double glazed windows with stone heads, jambs and sills. In fair condition. |  | Allow for cleaning and cyclical redecoration of timber frames. | [5 empty] | incl |  |  |  | incl
3.3 | Communal door West Elevation | Timber framed double door with double glazed units inset. In fair condition. |  | Allow for cleaning and cyclical redecoration. | [5 empty] | Incl |  |  |  | Incl
3.4 | Doors West Elevation | 2no timber doors to the west elevation are in fair condition. |  | Allow for cleaning and cyclical redecoration. | [5 empty] | Incl |  |  |  | Incl
3.5 | Communal door East Elevation | Timber framed double door with inset glazing. |  | Allow for cleaning and cyclical redecoration. | [5 empty] | Incl |  |  |  | Incl
4 | M&E
4.1 | Lighting | Surface fixed background lighting. Satisfactory condition. |  | Consider replacement within 10 years. | [6 empty] | 2000 |  |  |  | Provisional sum
5 | INTERNALLY
5.1 | Decoration | Painted plaster finish to ceilings, columns and walls. | B | Undertake cyclical decoration. | 2CI |  |  |  | 6500 |  |  |  |  | 6500
5.2 | Floors | Carpet floor covering with entrance barrier matting upon entry point. | B | Allow for periodic replacement. | 2CI | [7 empty] | 5500
5.3 | Joinery | 4no painted solid core fire doors. Satisfactory condition. | B | Undertake cyclical decoration. We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500 |  |  |  |  | Incl |  |  | Incl
TOTALS: | [5 empty] | 6750 | 2000 | 2750 | 13250 | 16750 | 9000 | 4000 | 7500 | 35250

## Victoria
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Victoria
Item Ref. | Element / Location | Condition and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition with several slipped and damaged slates noted. The tiles are generally soiled. | B | Allow for safe access to undertake repairs to slipped slates and carry out a general roof inspection. | 2CI |  | 1500 |  | 1500 |  | 1500 |  | 1500 | 1500 | Allowance for independent section of scaffold for to undertake isolated repairs. Sum allowed to contribute to budget total.
1.2 | Roof | 2no flat roof sections to the turret elevations. Assumed bituminous mineral felt covering. East elevation currently undergoing repair works and weatherproofing. West elevation appears to be in fair condition. | B | Felt covering will experience solar degradation over the coming 10 year term. Reactive works will be required. | 2CI |  |  |  | 4500 |  |  |  |  | 3000
1.3 | Roof | Concrete ridge tiles have been repaired using a dry ridge system. Appear in good order. | B | Slight algae growth. No works anticipated within the reporting years | 3CII
1.4 | Roof | Lead valleys are in fair condition and commensurate with age. | B | Reactive works estimated for repairs over the term. | 2CI |  |  |  | 1500 |  |  |  | 1500
1.5 | Roof | Stone coping and kneeler stones. Appear in fair condition. | B | No defects identified from aerial footage. Recommend pull test when safe access equipment is available. | 2CI |  |  |  | 1000
1.6 | Skylights | 12No Velux type rooflights across all roof pitches. Appear aluminium from drone footage. No visible defects from footage. | B | No works anticipated during the reporting years. | 2CI
1.7 | Chimneys | 4no coursed stone chimneys with dressed crowns and clay pots. Generally in satisfactory condition through out. | B | Undertake regular review with access imagery. Monitoring of the chimney pots should be regularly undertaken. | 2CI
1.8 | Rainwater goods | Powder coated pressed aluminium gutters and steel downpipes. Satisfactory condition. | B | Allow for all joints to downpipes to be re sealed. | 1CI |  |  |  |  | 2500 |  |  |  | 2500 | MEWP access allowed for.
1.9 | Facias and Soffits | Painted Timber fascia's. In poor condition paint flaking. | B | Allow for cyclical decorations. | 1CI |  | 2400 |  |  |  | 2400 |  |  | 2400
2 | WALLS
2.1 | Walls (all elevations) | Stone walling. In fair condition. Sporadic missing pointing. Some staining noted to stonework. | B | Allow for circa 10sqm of re-pointing. | 1CI |  | 500 |  | 500 |  | 500 |  | 500 | 1000 | Ensure correct mortars are used.
2.2 | Walls | Stone walling with stone copings forming external staircase to the ground floor. | B | Allow for cyclical re-pointing and repairs. | 2CI |  | 250 |  |  |  | 250
3 | WINDOWS AND DOORS
3.1 | Windows | Painted timber sliding sash window casements with trickle vents. In fair condition. | B | Allow for cleaning and cyclical redecoration. | 1CI |  |  |  | 10500 |  |  |  | 10500 | 10500
3.2 | Door | 2no Painted timber doors with brass handles. | B | Allow for cleaning and cyclical redecoration. | 1CI |  |  |  | 250 |  |  |  | 250 | 250
4 | INTERNALLY
4.1 | Decoration | Painted plaster generally in good condition. Timber work also in good condition. | B | Allow for cyclical decoration. | 2CI | [5 empty] | 3500 |  |  | 3500
4.2 | Flooring | Small section of barrier matting at the entrance is in good condition, carpet to other areas is in fair condition throughout, showing minor signs of wear. | B | Replace periodically and allow for regular cleaning. | 2CI |  |  | 4500 | [5 empty] | 4500
4.3 | Joinery | Timber fire door to meter cupboard. Satisfactory condition. | B | Undertake cyclical decoration. We advise that a fire door inspection survey is undertaken periodically to capture repairs required. | 1BIII | 500 |  | Incl | [5 empty] | Incl
TOTALS: | [5 empty] | 500 | 4650 | 4500 | 19750 | 2500 | 8150 | 0 | 14250 | 29150

## Cliffe
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Cliffe
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
Only the central core of the building was surveyed as requested.
1 | ROOF
1.1 | Roof | Natural slate roof covering. Generally in fair condition with approx. 2no slipped slates across the roof. Mainly to the chimney aperture. The tiles are generally soiled. | B | Allow for safe access to undertake repairs to slipped slates and carry out a general roof inspection. | 2CI |  |  |  | 7500 |  |  | 3500 |  |  | Repairs to the roof covering will require scaffolding. We recommend that works are grouped together across the roof to make the cost of scaffold erection efficient. We have allowed for a small section of scaffold to access the central roof. Edge protection will need to be evaluated.
1.2 | Roof | Concrete ridge tiles have been laid and fixed with a dry ridge system. No defect noted.
1.3 | Roof | Lead valleys are in satisfactory condition throughout.
1.4 | Roof | Stone coping & kneeler stones. No defects noted. | B | A pull test is recommended during routine maintenance of this roof. This will ensure no lose stonework. | 1BIII |  |  |  | 1500 | [5 empty] | Advise this is carried out when access scaffolding is erected to the building as a safety precaution.
1.5 | Chimney | Coursed stone construction with mortar flaunching to the crown. No defect noted. | B | Recommend close inspection next time scaffold is erected. | 3CI |  |  |  | 250
1.6 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and downpipes. Satisfactory condition. | B | Allow for all joints to downpipes and gutters to be re sealed. | 2CI |  |  |  | 2500
1.7 | Fascia's & Soffits | Painted timber. Commensurate with age. | B | Allow for cyclical decorations. | 2CI |  |  |  | 1500 |  |  |  | 1500
2 | WALLS
2.1 | Walls North | Natural walling stone with dressed lintels and cills. Pointing has failed across several locations at high level. | B | Repoint areas where pointing has failed. | 1CI |  | 1500 |  |  |  |  | 1500 |  |  | Cherry picker access allowed for to the front elevation only.
2.2 | Walls North | Large area of concrete render. Satisfactory condition. Appears to have been recently redecorated. | A | Allow for cyclical redecoration. | 2CI |  |  |  | 1500 |  |  |  | 1500
2.3 | Walls North | Timber slat infill cladding. Satisfactory condition. Requires redecoration. | C | Allow for cyclical redecoration. | 2CI |  | 2500 |  |  |  | 2500 |  |  |  | Cherry picker access allowed for to the front elevation only.
2.4 | Walls East | Natural walling stone with dressed lintels and cills. No defect.
2.5 | Walls East | Timber slat infill cladding. Satisfactory condition. Requires redecoration. | C | Allow for cyclical redecoration. | 2CI |  | incl
2.6 | Walls South | Natural walling stone with dressed lintels and cills.
2.7 | Walls South | Timber slat infill cladding. Satisfactory condition. Requires redecoration. | B | Allow for cyclical redecoration. | 2CI |  |  | 10500 |  |  |  | 10500 |  |  | This elevation would need scaffold access to the rear gardens. Window decoration should be considered at this stage.
2.8 | Walls West | Natural walling stone with dressed lintels and cills. No defect.
3 | WINDOWS & DOORS
3.1 | Windows North | Timber sliding sash casements. Paint finish has deteriorated in isolated locations and the mastic seal has perished throughout. | B | Allow for cyclical redecoration and replacing mastic seals to window perimeters. | 1CI |  |  | 4500 |  |  |  | 4500 |  |  | Cherry picker access allowed for.
3.2 | Doors North | Timber painted entrance door with vision glazing panels. | B | Allow for cyclical redecoration. | 1CI |  |  | 150 |  |  |  | 150
3.3 | Windows East | Timber sliding sash casements. Paint finish has deteriorated in isolated locations and the mastic seal has perished throughout. | B | Allow for cyclical redecoration and replacing mastic seals to window perimeters. | 1CI |  |  | 4500 |  |  |  | 4500
3.4 | Windows South | Timber sliding sash casements. Paint finish has deteriorated in isolated locations and the mastic seal has perished throughout. | B | Allow for cyclical redecoration and replacing mastic seals to window perimeters. | 1CI |  |  | 4500 |  |  |  | 4500 |  |  | Scaffold access allowed in above item. Walls South.
3.5 | Doors South | Timber painted fire escape door. | B | Allow for cyclical redecoration. | 1CI |  |  | 150 |  |  |  | 150
3.6 | Windows West | Timber sliding sash casements. Paint finish has deteriorated in isolated locations and the mastic seal has perished throughout. | B | Allow for cyclical redecoration and replacing mastic seals to window perimeters. | 1CI |  |  | 350 |  |  |  | 350
4 | M&E
4.1 | Lighting | Surfaced fixed background lighting. Satisfactory condition. | B | Consider replacement within 10 years. | 2CI | [8 empty] | 2000 | Provisional sum.
5 | INTERNALLY
5.1 | Decoration | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. | 2CI |  |  |  | 4800 |  |  |  |  | 4800
5.3 | Floor covering | Ribbed carpet covering. Satisfactory condition. | B | Advise replacement will be required over the next 10 years. | 2CI | [8 empty] | 3500
5.4 | Joinery | Timber fire exit doors with Georgian wired vision panels. Satisfactory condition. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs. | 1BIII |  | 500
TOTALS: | [5 empty] | 0 | 4500 | 24650 | 19550 | 0 | 2500 | 29650 | 3000 | 10300

## Pevril
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Pevril
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF
1.1 | Roof | Dual pitched natural slate roof covering with a flat roof section separating each pitch. The roof is generally in fair condition. New leadwork appears to have oxidised causing staining to the slate covering prominently to chimney flashings. | B | No defect noted. Reactive maintenance budget allowed. | 2CI |  |  | 2000 |  | 2000 |  | 2000 |  | 4000 | Isolated access tower allowed for to repair.
1.2 | Roof | Bituminous mineral felt roof with 3no polycarbonate lantern / light wells. Historic repairs evident to the felt in this are where service penetrations have been made. | B | Allowance for reactive maintenance. | 2CI |  |  | 1000 |  | 1000 |  | 1000 |  | 2000
1.3 | Roof | Concrete ridge tiles have been laid and fixed with a dry ridge system. No defect noted.
1.4 | Roof | Leadwork is in satisfactory condition throughout. No defect noted. | B | Allow for general repairs. | 2CI |  |  | 500 |  |  |  | 500
1.5 | Roof | Stone coping & kneeler stones. Appear in satisfactory condition from drone footage. A small section to the North elevation have been weatherproofed with a liquid waterproofing system. | B | A pull test is recommended during routine maintenance of this roof. This will ensure no lose stonework. | 1BIII |  |  | 1000 | [6 empty] | This element will need isolated scaffolding. We advise this is undertaken when scaffold is erected for roof / gutter repairs.
1.6 | Chimneys | Coursed stone construction with mortar flaunching to the crown. No defect noted. Algae growth evident. | B | Undertake close inspection when scaffolding is next erected. | 2CI |  |  | 500
1.7 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and downpipes. Isolated areas of staining to joint lines. | B | Allow for all joints to gutters and downpipes to be re sealed. | 1CI |  |  | 15000 | [6 empty] | Scaffold Incl
2 | WALLS
2.1 | Walls North | Natural stone construction with ashlar dressed lintels, cills and jambs. The stone is delaminating and is showing heavy signs of erosion to the face of the stonework. Over time, the stonework has been re pointed with Portland based mortars which have accelerated the erosion process. There is also large areas of missing pointing to the general elevation. | C | Investigate further with stone specialist such as. (Medusa Stone - Nick Laurence nicklaurence@medusastonemasonry.com). Stone replacements or repairs may be most cost efficient but a specialist is required due to the severity on this building. | 1CI | [9 empty] | No cost allowed as further investigation work is required. We advise this is sort asap to prevent further deterioration.
2.2 | Walls East | As above. |  | As above.
2.3 | Walls South | As above. |  | As above.
2.4 | Walls West | As above. |  | As above.
3 | WINDOWS & DOORS
3.1 | Windows North | Timber sliding sash casements. Paint finish has deteriorated in isolated locations. | B | Allow for cyclical redecoration. | 1CI |  |  | 750 |  |  |  | 750 |  | 750
3.2 | Windows East | Timber sliding sash casements. Paint finish has deteriorated in isolated locations. Isolated window repairs may be required when paint stripped. | B | Allow for cyclical redecoration and isolated repairs to timber casements. | 1CI |  |  | 5500 |  |  |  | 5500 |  | 5500
3.3 | Windows South | Timber sliding sash casements. Paint finish has deteriorated in isolated locations. | B | Allow for cyclical redecoration. | 1CI |  |  | 750 |  |  |  | 750 |  | 750
3.4 | Doors East | 2no timber entrance doors. Paint finish is beginning to deteriorate. | B | Allow for cyclical redecoration. | 1CI |  |  | 250 |  |  |  | 250 |  | 250
3.5 | Windows West | Timber sliding sash casements. Paint finish has deteriorated in isolated locations. | B | Allow for cyclical redecoration. | 1CI |  |  | 5500 |  |  |  | 5500 |  | 5500
3.6 | Doors South | 1no timber painted entrance door. | B | Allow for cyclical redecoration. | 1CI |  |  | 250
3.7 | Windows West | Timber sliding sash casements. Paint finish has deteriorated in isolated locations. | B | Allow for cyclical redecoration. | 1CI |  |  | 3500
4 | M&E
4.1 | Lighting | Surfaced fixed background lighting. Satisfactory condition. | B | Consider replacement within 10 years. | 1CI | [8 empty] | 2000 | Provisional Sum.
5 | INTERNALLY
5.1 | Decoration | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. | 2CI |  |  |  |  | 5500
5.2 | Floor covering | Ribbed carpet covering to hall ways and stairs. Satisfactory condition. | B | Advise replacement will be required over the next 10 years. | 2CI |  |  |  |  | 4500
5.3 | Joinery | Painted timber fire exit doors with Georgian wired glazing. Satisfactory condition. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs. | 1BIII |  | 500
TOTALS: | [5 empty] | 0 | 500 | 36500 | 0 | 13000 | 0 | 16250 | 0 | 20750

## Edward
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Edward
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | ROOF | [13 empty] | Only the central core of the building was surveyed as requested.
1.1 | Roof | Natural slate roof covering. Generally in fair condition with 1no slipped slate into the gutter. The tiles are generally soiled and evidence that several tile replacements have been undertaken historically. | B | Allow for safe access to undertake repairs to 1no slipped slates and carry out a general roof inspection. | 2CI |  | 500 | [7 empty] | Repairs to the roof covering will require scaffolding. We recommend that works are grouped together across the roof to make the cost of scaffold erection efficient.
1.2 | Roof | Concrete ridge tiles have been re bed onto a dry ridge system. Mortar has detached to the horizontal joint line to isolated areas. No defects noted.
1.3 | Roof | Chimney breast appears in satisfactory condition. Debris have collected behind the valley. Stone erosion is also evident to the facing stone. | B | Remove debris from valley and undertake general inspection of crown and stonework. | 2CI |  | 500 | [7 empty] | Advise this is picked up when access scaffold is erected for works to the gutters.
1.4 | Roof | Leadwork is in satisfactory condition. No defects.
1.5 | Roof | Stone coping & kneeler stones. Appear in satisfactory condition from drone footage. | B | A pull test is recommended during routine maintenance of this roof. This will ensure no lose stonework. | 1BIII |  | 1000 | [7 empty] | Undertake when access is available.
1.6 | Rainwater goods | Powder coated pressed aluminium gutters, hoppers and downpipes. Isolated area of staining to joint lines. | B | Allow for all joints to gutters and downpipes to be re sealed. | 1CI |  | 8000 | [7 empty] | Scaffold to central core allowed.
1.7 | Fascia's | Painted timber. Commensurate with age. | B | Allow for cyclical decorations. | 1CI |  | 500
2 | WALLS
2.1 | Walls North (Entrance) | Natural stone construction with ashlar dressed lintels, cills and jambs. The stone is delaminating and is showing heavy signs of erosion to the face of the stonework. Isolated areas of missing pointing to the general elevation. | B | Allow for repointing at low level. Allow for 10m2. Refer to comments for Pevrill regarding the condition of the facing stone. | 1CI |  | 450 | [7 empty] | Stone specialist required.
2.2 | Walls East | Natural stone construction with ashlar dressed lintels, cills and jambs. Evidence of historic stonework repairs to the rear side. |  | As above.
2.3 | Walls South | Natural stone construction with ashlar dressed lintels, cills and jambs. Large feature dressed stone. |  | As above.
2.4 | Walls West | Natural stone construction with ashlar dressed lintels, cills and jambs. Isolated areas of missing pointing to the general elevation and evidence of previous pointing repairs. |  | As above.
3 | WINDOWS & DOORS
3.1 | Windows North | Timber sliding sash casements. Paint finish has flaked throughout. Window joint pointing / mastic has perished and detached. | B | Allow for cyclical redecoration and isolated repairs to timber casements. Mastic required to joints. | 1CI |  | 1500 |  |  |  |  | 1500 |  |  | Tower scaffold allowed.
3.2 | Doors North | Timber painted entrance door with glazed vision screens to perimeter. Satisfactory condition although the lock mechanism was faulty. | B | Repair locking mechanism. Allow for cyclical redecoration. | 1AI | 250 |  |  |  | 150
3.3 | Windows East | Timber sliding sash casement. Paint finish has flaked throughout. Window joint pointing / mastic has perished and detached. | B | Allow for cyclical redecoration and isolated repairs to timber casements. Mastic required to joints. | 1CI |  | 750 |  |  |  |  | 750
3.4 | Windows South | Timber sliding sash casements. Paint finish has flaked throughout. Window joint pointing / mastic has perished and detached. | B | Allow for cyclical redecoration and isolated repairs to timber casements. Mastic required to joints. | 1CI |  | 1500 |  |  |  |  | 1500
3.5 | Doors South | Large solid core timber door with glazed vision screens to perimeter. Emergency exit ironmongery operational. | B | Allow for cyclical redecoration. | 1CI | 150 |  |  |  | 150
4 | M&E
4.1 | Lighting | Surfaced fixed background lighting. Satisfactory condition. | B | Consider replacement within 10 years. | 2CI | [8 empty] | 2000 | Provisional Sum.
5 | INTERNALLY
5.1 | Decoration | Painted plaster finish. Satisfactory condition throughout. | B | Allow for cyclical redecoration. | 2CI |  |  |  | 3500
5.2 | Floor covering | Ribbed carpet covering throughout. Satisfactory condition. | B | Advise replacement will be required over the next 10 years. | 2CI | [8 empty] | 3500
5.3 | Joinery | Timber fire exit doors with vision panel to GF. Satisfactory condition. | B | We advise that a fire door inspection survey is undertaken periodically to capture repairs. | 1BIII |  | 500
TOTALS: | [5 empty] | 400 | 15200 | 0 | 3500 | 300 | 0 | 3750 | 0 | 5500

## Garages
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Garages 0-7
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
1 | GARAGE 1
ROOF
1.1 | Roof | Natural slate covering. No defects. | B | Allowance for general repairs. | 2CI | [6 empty] | 500
1.2 | Roof | Dry ridge tile system. No defects | B
1.3 | Roof | Stone coping stones and kneelers. Liquid waterproofing has been applied to the coping stones. | B | No further works required over term. | 2CI
1.4 | Rainwater goods | Pressed aluminium gutters and downpipes. Fully choked with vegetation debris. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. Leaf guards can be installed. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
1.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. Included above. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
1.6 | Walls general | Stone walls with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. | B | Replace pointing with a mastic rather than mortar. | 2CI | 500 | [7 empty] | 500
DOORS
1.7 | Garage doors | 7no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 3CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
2 | GARAGE 2
ROOF
2.1 | Roof | Natural slate covering. No defects. | B | Allowance for general repairs. | 2CI | [6 empty] | 500
2.2 | Roof | Dry ridge tile system. No defects. | B
2.3 | Roof | Stone coping stones and kneelers. No defects noted. | B
2.4 | Rainwater goods | Pressed aluminium gutters and downpipes - satisfactory condition. |  | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
2.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. |  | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
2.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. | B | Replace pointing with a mastic rather than mortar. | 2CI | 500 | [7 empty] | 500
2.7 | Walls - meter cupboard | Natural stone cupboard with bituminous mineral felt covering. Walls are detaching from the main garage structure. | B | Re point the joint to the main garages. Allow for monitoring this movement to see if further remedial works are required to the foundation of the cupboard. | 1CI | 250
DOORS
2.8 | Garage doors | 3no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
3 | GARAGE 3
ROOF
3.1 | Roof | Natural slate covering. Isolated slipped slates. | B | Undertake slate repairs with safe access tower scaffold. | 2CI | 500 | [5 empty] | 500
3.2 | Roof | Dry ridge tile system. No defects | B
3.3 | Roof | Stone coping stones and kneelers. | B
3.4 | Rainwater goods | Pressed aluminium gutters and downpipes. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
3.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
3.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. Cracked art stone lintel. | B | Replace pointing with a mastic rather than mortar. Monitor the cracked lintel. Stone repair can be undertaken. | 2CI | 500 | [7 empty] | 500
DOORS
3.7 | Garage doors | 3no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
4 | GARAGE 4
ROOF
4.1 | Roof | Natural slate covering. Isolated slipped slates. | B | Undertake slate repairs with safe access tower scaffold. | 2CI | 500 | [5 empty] | 500
4.2 | Roof | Dry ridge tile system. No defects | B
4.3 | Roof | Stone coping stones and kneelers. | B
4.4 | Rainwater goods | Pressed aluminium gutters and downpipes. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
4.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
4.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. | B | Replace pointing with a mastic rather than mortar. | 2CI | 500
4.7 | Walls to bin store | Timber fence panels. | B | Allow for cyclical redecoration. | 2CI |  | 300 |  |  |  | 300 |  |  | 300
DOORS
4.8 | Garage doors | 3no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
5 | GARAGE 5
ROOF
5.1 | Roof | Natural slate covering. No defects. | B | Allowance for general repairs. | 2CI |  | 500 |  |  |  |  | 500
5.2 | Roof | Dry ridge tile system. No defects | B
5.3 | Roof | Stone coping stones and kneelers. | B
5.4 | Rainwater goods | Pressed aluminium gutters and downpipes. Gutters leaking during inspection. Hedgehog gutter guard installed. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
5.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
5.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. DPC exposed to the rear elevation with many piercings. | B | Replace pointing with a mastic rather than mortar. Replace section of DPC with new and tape secure. | 1CI | 2000
5.7 | Walls electric cupboard. | Stone walls butted to main garage structure. Mineral felt roof covering and timber doors. Doors require painting. | B | Re decorate timberwork. | 2CI | 150 | [5 empty] | 150 |  | 150
DOORS
5.8 | Garage doors | 3no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
6 | GARAGE 6
ROOF
6.1 | Roof | Natural slate covering. No defects. | B | Undertake slate repairs with safe access tower scaffold. | 2CI | 500 | [5 empty] | 500
6.2 | Roof | Dry ridge tile system. No defects | B
6.3 | Roof | Stone coping stones and kneelers. | B
6.4 | Rainwater goods | Pressed aluminium gutters and downpipes. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
6.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
6.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. | B | Replace pointing with a mastic rather than mortar. | 2CI | 500 | [7 empty] | 500
6.7 | Walls electric cupboard. | Stone walls butted to main garage structure. Mineral felt roof covering and timber doors. Doors require painting. | B | Allow for cyclical redecoration. |  | 150 | [5 empty] | 150 |  | 150
DOORS
6.8 | Garage doors | 4no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
7 | GARAGE 7
ROOF
7.1 | Roof | Natural slate covering. No defects. | B | Undertake slate repairs with safe access tower scaffold. | 2CI | 500 | [5 empty] | 500
7.2 | Roof | Dry ridge tile system. No defects | B
7.3 | Roof | Stone coping stones and kneelers. No defects. | B
7.4 | Rainwater goods | Pressed aluminium gutters and downpipes. | B | Allow for cyclical maintenance due to the location of the garage and the foliage present. | 1CI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
7.5 | Fascia's & Soffits | Painted timber fascia. Paint is flaking. | B | Allow for cyclical redecoration. | 1CI | incl |  | incl |  | incl |  | incl |  | incl
WALLS
7.6 | Walls general | Stone wall with art stone lintels to the garage door openings. Pointing has detached from the lintel / art stone joint line. | B | Replace pointing with a mastic rather than mortar.
7.7 | Walls electric cupboard. | Stone walls butted to main garage structure. Mineral felt roof covering and timber doors. Doors require painting. | B | Allow for cyclical redecoration. | 1CI | 150 | [5 empty] | 150 |  | 150
DOORS
7.8 | Garage doors | 4no steel powder coated doors. Satisfactory condition - soiled finish. | B | Allow for cyclical cleaning. | 2CI | incl | incl | incl | incl | incl | incl | incl | incl | incl
TOTALS: | [5 empty] | 8950 | 2550 | 1750 | 1750 | 1750 | 2050 | 5700 | 1750 | 4500

## Hardstandings
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working/Living environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Hardstandings
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
| EXTERNALLY | [13 empty] | General condition of the hardstandings require ongoing monitoring and reactive maintenance actioned.
1.1 | Alexandra Apartment parking | Stone mastic asphalt hardstandings. In fair condition. No defects. | B
1.2 | Osborne Mews Road | Stone mastic asphalt hardstandings. Cracking noted around 2no manhole covers. In fair condition. | B | Allow for patch repairs when required to traffic worn areas. | 2CI | [8 empty] | 6000
1.3 | Osborne Mews Road | Stone mastic asphalt hardstandings. Cracking noted around 1no gully. In fair condition. | B | Allow for patch repairs when required. | [9 empty] | incl
1.4 | Osborne Mews Road | Concrete flagstones. Cracking noted to 3no flagstones. Staining to flags. In fair condition. | B | Lift and replace cracked flagstones. Allow for cyclical jet washing. | 2CI |  | 500 |  |  |  | 500
1.5 | Sheaf 2 and 3 | Concrete flagstones. Staining noted to flags. In fair condition. | B | Replace when damage occurs. Allow for cyclical jet washing. | 2CI |  | 500 |  |  |  | 500
1.6 | West Alexandra Building | Tarmacadam path, some spalling adjacent to paving to the East elevation of Sheaf 1. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 1500
1.7 | West Alexandra Building | Block paving, some sunken areas to the East elevation of Sheaf 1. Block paving is in fair condition but is soiled. | B | Take up and re-lay sunken paving. 2ms. Allow for cyclical jet washing. Allow for reactive repairs to block pavers during term. | 1BI | 250 |  |  | 250 |  |  | 250 |  | 250
1.8 | Osborne Walk | Stone mastic asphalt, surface heavily soiled and in poor condition with spalled and cracked areas. | B | Undertake cyclical jet washing to reduce slip hazard. | 1BI | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 450
1.9 | Osborne Walk | Concrete flagstones set within soft landscaping. Slightly soiled but in fair condition. | B
2 | Osborne Walk | Retaining wall is in very poor condition and is leaning considerably. Bulging evident throughout. | C | We advise a defect report is undertaken in conjunction with a Structural Engineer to provide a remedial specification. | 1BI | 1500
2.1 | Casual Cottages | Stone mastic asphalt, surface showing signs of wear with spalled and cracked areas. Generally in fair condition. | B | Allow for patch repairs when required. | [9 empty] | 2000
2.2 | Kingswood East | Stone mastic asphalt path. Spalling and cracking noted around 7no inspection chambers. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 1BI | [8 empty] | 3500
2.3 | Kingswood Apartments North | Stone mastic asphalt, surface showing signs of wear with some pitted, spalled and cracked areas. In fair condition. | B | Allow for patch repairs when required. | 2CI | [8 empty] | 2000
2.4 | Kingswood Apartments South | Tarmacadam surface. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 3000
2.5 | Union Drive | Stone Mastic asphalt hardstanding. Minor breakdown of SMA, pooling noted to areas where patch repairs have been undertaken. In fair condition. | B | Allow for patch repairs when required. Heavy traffic estimated due to this been the site entrance. | 2CI |  |  |  |  | 5000 |  |  |  | 2500
2.6 | Edward Apartments | Stone mastic asphalt hardstanding. Area of historic replacement surface noted. SMA showing minor surface breakdown with some spalled and cracked areas. In fair condition. | B | Allow for patch repairs when required. | 2CI | [8 empty] | 2500
2.7 | Edward Apartments | Moss growth noted around metal ACO channel to the front of the garages. | B | Allow for cyclical jet washing. Included when the garage doors are scheduled to be cleaned. | 2CI | Incl
2.8 | Pevril Apartments West | Stone mastic asphalt hardstanding displaying minor surface breakdown with some spalled areas. In fair condition. | B | Allow for patch repairs when required. | 2CI | [8 empty] | 1000
2.9 | Pevril Apartments South | Stone mastic asphalt hardstanding displaying minor surface breakdown with some spalled areas. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing due to tree canopy cover. | 1BI | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 750
3 | Victoria apartments | Stone mastic asphalt hardstanding displaying minor surface breakdown with some spalled areas. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 3500
3.1 | Victoria apartments | Concrete flagstones. Some staining to flags. In fair condition. | B | Replace when required. Allow for cyclical jet washing. | 2CI | 300 |  | 300 |  | 300 |  | 300 |  | 600
3.2 | Victoria Court | Stone mastic asphalt road displaying minor surface breakdown with some spalled areas. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 4000
3.3 | Hardstanding to garage 4. | Block paving is soiled with moss growth to junctions. Build up of debris noted adjacent to the drain. | B | Replace when required. Allow for cyclical jet washing. | 2CI | [8 empty] | Incl
3.4 | Kingswood Gardens | Stone mastic asphalt paths. In fair condition. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 5000
3.5 | Alexandra Gardens | Stone mastic asphalt path displaying minor surface breakdown with some cracked, spalled and pitted areas. In fair condition. Stone mastic asphalt around 5no manhole covers is spalled and cracked to the road. | B | Allow for patch repairs when required. Allow for cyclical jet washing. | 2CI | [8 empty] | 2000
3.6 | Line marking | In fair condition. | B | Allow for cyclical relining of the site line markings. | 2CI |  | 750 |  | 750 |  | 750 |  | 750 | 750
3.7 | Security Cameras | Circa 12no security cameras. In fair condition. | B | Allow for cyclical redecoration and replacement of faulty cameras. Work has recently been undertaken. | 2CI |  |  |  | 7500 |  |  |  |  | 7500
3.8 | Pole mounted street lights | Circa 36no pole mounted street lights. In fair condition. | B | Allow for redecoration and replacement of light fittings as required. Bulbs changed to LED in 2019. | 2CI | [8 empty] | 1000
3.9 | Small street lights around paths. | Circa 35no small street lights in fair condition generally. 1no light is damaged. | B | Repair damaged light fitting. Allow for repairs when required. Allow for redecoration and replacement of light fitting. | 1CI | 250 | [7 empty] | 5000
4 | Bin Stores | 8no timber bin stores. | B | Allow for cyclical redecoration. | 2CI |  | 3000 |  |  | 3000 |  |  | 3000 | 3000
TOTALS: | [5 empty] | 800 | 4000 | 550 | 8500 | 8550 | 1000 | 550 | 4000 | 47600

## Boundarys
Budget cost at time of survey (excluding professional fees and VAT)
CONDITION CATEGORIES
|  |  | A = New |  | PRIORITIES |  |  |  | SUB PRIORITY |  |  | EFFECT IF DEFERRED
|  |  | B = Minor Deterioration |  | Priority 1 = Essential |  |  |  | A = To meet statutory obligations |  |  | I = Increase in eventual remedial costs and ongoing disruption to operations
|  |  | C = Operational but requiring Major Repair or Replacement |  | Priority 2 = Desirable Priority 3 = Discretionary |  |  |  | B = To meet H & S requirements C = To prevent deterioration |  |  | II = Reduction in quality of working environment III = Possible injury or health hazard
D = Serious risk of imminent breakdown
X = When added to C or D that total replacement only real alternative
Planned Maintenance Schedule - Boundary
Item Ref. | Element / Location | Description and Defect Analysis | Con. Cat. | Defect Solution | Priority | Backlog (2019) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2030 | Comments
EXTERNALLY
| Osbourne Road | [13 empty] | Assume speech and language building is not included in the areas surveyed.
1.1 | Upward of the vehicle gates | Painted iron railings, colour fading | B | Undertake cyclical decorations | 1CI |  |  | 3000 |  |  |  | 3000 |  | 3000 | Assume Sub Station is Northern Power responsibility for maintenance.
1.2 |  | Vehicle automated gates | B | Undertake periodic servicing. | 1BIII |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
1.3 |  | Manual pedestrian gate | B | Undertake cyclical decorations, cost included above. Note condition of paint is worse than the railings and maybe considered to be undertaken ahead of the railings being painted. | 1CI | 50 |  | Incl. |  |  |  | Incl. |  | Incl
Downhill from gates
1.4 |  | Stone wall is in a fair condition but weeds and self setting seeds are embedded in the mortar. Algae growth to the coping. | B | Remove weeds, apply weed killer to whole surface and undertake isolated repointing. | 1CI | 200 |  |  | 250 |  |  | 250 |  | 250 | Allowance for future works
1.5 |  | Defective pointing to stone work. | B | Allowance for 5m2 annual maintenance to areas that become defective. | 1CI | 120 |  | 120 |  | 120 |  | 120 |  | 240
1.6 |  | Areas of wall with slight lean | B | No works anticipated during reporting years. Allow for annual review. | 1CI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | Step crack to corner between Union Road, potentially due to tree roots. | B | Liaise with a tree surgeon to limit impact on the wall from the tree. Undertake localised pointing repairs. | 1CI | 320 |  | 120 |  | 120 |  | 120 |  | 120
Union Road
1.8 |  | Shared gates with the NHS | B | Undertake cyclical redecoration | 1CI | 420 |  | 420 |  |  |  | 420 |  | 420 | Can a proportion be paid by the NHS as part of their lease and service charge??
1.9 |  | Algae growth to the stone wall towards Lyndhurst Road | B | Remove algae growth, apply weed killer and undertake periodic repointing as and when it is required. | 1CI | 250 |  |  | 250 |  |  | 250 |  | 250 | Allowance for future works
1.1 |  | Overhanging trees to the corner of Lyndhurst Road | B | Undertake pruning to remove branches overhanging the highway. | 1CI | 200
Lyndhurst
1.11 |  | Ivy and foliage spreading over stone wall | B | Cut back and or maintain. Foliage has an impact on the condition of the stone and mortar. | 1CI | 100
1.12 |  | Vehicle automated gates | B | Undertake periodic servicing. | 1BIII |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
1.13 |  | Stone wall pointed with incorrect mortar to LHS of the gates, which will cause damage to the stone. | B | Hack out portland cement and reinstate with lime based mortar | 1CI | 400 |  |  | 250 |  |  | 250 |  | 250 | Allowance for future works
Wall behind Sheaf
1.14 |  | 1No expansion joint can be seen. | B | Rake out and replace when it becomes stiff and/or brittle. | 1CI |  |  |  | 60
1.15 |  | Railings | B | Undertake cyclical redecoration | 1CI |  |  | 800 |  |  |  | 800 |  | 800
1.16 |  | Timber fence to gardens | B | Who is responsible for repair and maintenance, no access gained. | 1CI | [9 empty] | No access gained.
| Sheaf cul de sac | [13 empty] | Assume stone wall forms part of the demise, but extent of timber fence ownership is not known.
1.17 |  | 3No expansion joints visible but may be more within private gardens. | B | Rake out and replace when it becomes stiff and/or brittle. | 1CI |  |  |  | 180
TOTALS: | [5 empty] | 2060 | 500 | 1960 | 1490 | 740 | 500 | 2710 | 500 | 2830